## Sheet1
Change Number | Planned Start Date & Time | Planned End Date & Time | Short Description | Business Units Impacted | Change Related CIs | Outage or Reboot Associated? | Can be Backed Out? | Other Market Validation Required? | Risk | Environment | Assigned Group Name | Full Name | Change State | Type
CHG06789519 | 2026/02/04 10:00:00 | 2026/02/06 22:00:00 | ESP to Stonebranch Migration for ESP event, PRODCONT | GCS, INV, USRM, GDS, CF, GRS | Stonebranch Workload Automation, MAINFRAME PLATFORM COMPUTE SERVICES | No | Yes, less than an hour | Yes | High | Production (Prod) | STONEBRANCH MIGRATION TEAM | Andrew Baldwin | SCHEDULED | Normal
CHG07038415 | 2026/02/05 19:00:00 | 2026/02/08 08:00:00 | Effort id # HDOSD-12886:LM Prod PATCH & REBOOT- Jan-2026-Week-1 | INV, GCS, CF, GRS, LIT, GLOBAL RISK SOLUTIONS - LII APAC, USRM, GDS, GRM E¦W | AM - REGIONAL AGENCY MANAGEMENT AND PLANNING (RAMP), OC - AGENCY INFORMATION ARCH., Liberator, AM-SPS DIAL, AM - WRS REAL-TIME SERVICES & EDELIVERY, Clipper, AM - CENTRAL AGENCY REPOSITORY (CAR), CI - CI PORTAL, Storage Services Tools, ENTERPRISE VULN MGMT. AUTOMATION SERVICES, Splunk SIEM, USCM FIN BATCH MIDRANGE, PUBLISHING FORMS DOMAIN, AM-AF ARRANGE FINANCIALS, Middle Market Operational Reporting, LM UNIVERSAL REINSURANCE SYSTEM, CI CLEARANCE, HS DATADOG, CM AUTO ID, ARMS Bill Scheduler, TOBE Collections Cash Remittance, CAR WEB SERVICES, ENTERPRISE INFORMATICA OPERATIONAL INSIGHTS (IOI), TRACS, CF SAP ROUTER, LDAP Internal Services, RSA TWO-FACTOR SERVICES, ADW CUSTOMER CONTRACT, CSOC FORENSICS STEP FUNCTION READ, GIS SECURITY APPS JBOSS STACK, Deploy Ops Utilities, Linux_Prod_Week1_PatchReboot, CENTRIFY LDAP PROXY, ALMS, MYSQL SHARED DBAAS, CM - Bocomp Plus, CBS - CHOICE BILLING SYSTEM, IMPERVA SECURESPHERE, TOBE Cash Remittance, GRMUS DATAPOWER - BACKUP, RAMP WEB SERVICES, AM-BLS BILLING SYSTEM, CLAIM CONSOLIDATED DATA SERVICES, NMWB - NM Workbench, ONESTOP UTILITIES, SAF - PEM (PROPERTY EXPERIENCE MART), WINDOWS AION RULES SERVICE, AM-RAMCAR, PCI DataPower, CENTRIFY SERVICES, SOC SIEM, Compass, SAF - HFS (HOME FREQUENCY AND SEVERITY), UNIX IDENTITY MANAGEMENT SERVICES, Linux_Prod_Week1_PatchOnly, Caliber, CI - Pool Reporting, WEBSPHERE MQ, PIDA, PINGFEDERATE, WATSON TNG, ENTERPRISE INFORMATICA POWERCENTER, VIA PAL Claims Correspondence, TACACS-RADIUS SERVICES, Linux_Prod_Week4_PatchOnly, LCW VDE COMPUTE ON-PREMISE, Publishing Print Services, SAF - AFS (AUTO FREQUNCY AND SEVERITY), CBS CASH REMITTANCE PROCESSOR, GRM GPFS SAS INFORMATICA, SYSLOG-NG, LDAP EXTERNAL SERVICES, CLAIMS FINANCIAL LOSS INTEGRATION (CFLI), AGENCY DATA SERVICES BATCH, CLAIMS DETAIL SERVICE SOE, CONVERGENCE GUI, AM-ACS AGENCY COMMISSION SYSTEM, SAF - PLA, ELECTRONIC CUSTOMER REGISTRATION (ECR), SPACEWALK, SPLUNK ENTERPRISE, DATABASE ID MAINTENANCE, MASTER PARTY INQUIRY SERVICE, MIDRANGE SERVER MAINTENANCE, DbID (Database Inventory), PI AGENCY DOWNLOAD PREFERENCE MANAGEMENT, Backup Services TSM, BigID, ENTERPRISE INFORMATICA TEST DATA MANAGEMENT (TDM), NETWORK ADMINISTRATION TOOLS, @Work Premium Audit Workstation, PINGACCESS, VIA PAL ClaimCenter, CI - DIAL2 Core Components, AM-DA BILLING DOMAIN ADAPTER, TRIPWIRE, NESSUS SERVICES, Legal Data Platform, ZSCALER PRIVATE ACCESS, APPLICATION CENTRIC INFRASTRUCTURE, MAINVIEW CONSOLE MANAGEMENT, Linux_Prod_Week2_PatchOnly, BILLS, VORMETRIC DATA SECURITY MANAGER SERVICES, vxpip-mm6eczxe, vxpip-u4pra8xh, vxpip-kanteruw, vxpip-586sazdx, axkip-cqdpmvv3, vxpip-hldape03, vxpip-56ydfadv, vxpip-hcentx03, vxpip-a5j5ph7s, vxpip-nu5wdnnz, sxpip-znjpdnqx, vxkip-aagwab05, vxkip-hsmwmq01, vxpip-hcedsc01, vxpip-hcentx01, patch, vxkip-hsphec01, vxpip-3r3ejgtu, vxpip-vtu7fksp, vxpip-hvorm001, vxpip-vbhshx2w, vxpip-cshwmq03, vxkip-hcentr01, vxpip-ewkret07, vxpip-8x2fbkyw, vxpip-hcentx02, vxpip-x7azmd5t, vxkep-z82a7b8r, vxpip-cshwmq02, vxpip-4ycszv8c, vxpip-slmid05, vxpip-rq6gndaj, vxkip-6swks5yj, sxpip-u5prhnwj, sxpip-yp4xhqbh, vxpip-nystz7va, vxpip-9nwf58qc, vxpep-kx37ugws, vxpip-mhqndeph, vxpip-hproxp01, sxpip-a3vvr9kq, axkip-cngdk4ob, vxpip-w3qpqftr, sxpip-zumhhxpp, vxkip-qk9c97gc, vxpip-ewkret05, vxpip-hsphec01, vxpip-hcnplm01, vxkup-ppcidp01, vxkip-4d672d8s, vxpep-slmid04, vxkep-ecapas16, sxpip-4vns9ksg, vxpip-3fzbakrw, sxpip-9pqzmy3y, vxpip-hngpes01, vxkip-bxqy9x7s, sxkip-wjfw27cp, vxpip-hmrsds01, vxsip-hnetop01, vxpip-h5tpc002, vxpip-pshrmq24, vxkep-slmid04, lxpip-hsecop01, vxpip-np9wnqbn, vxkip-7ftj58kq, vxkip-4ddt9u8z, axkip-cr63ws1x, vxpip-hproxp02, vxpip-ewkret04, sxpip-wwhn8bpv, vxpip-hsphec07, sxpip-bbasnqww, vxpup-ppcidp01, vxpip-wskrbt6e, axkip-cu6njgyh, vxkip-86x4dpxy, sxpip-y8xvbr5g, vxkip-hproxp04, vx-eatkntn-p02p, axkip-ck5cc4v2, axkip-cmojgpz3, vxkep-ecapas23, vxpip-r8btnm9u, vxkep-ecapas02, vxkip-hmrspf07, sxpip-vu2af9yr, vxpip-htphgy01, vxpip-hngper02, vxpip-cshwmq01, vxkip-ashwmq01, vxpep-ecapas03, vxpep-qs5c43ry, vxkip-hmrspf08, axkip-c0au2yni, vxkip-hldapi02, axpip-cnjpucge, vxpip-esaapp02, vxpip-xqec86kb, vxpip-hngper04, sxpip-w56xtwwb, vxkep-ecapas22, vxpip-ppmfin02, axkip-c71adu7p, vxkip-hngpes04, vxkep-ecapas11, axkip-ce1qhjle, vxpip-uvghdj8s, vxpip-fg9rfs6e, vxpip-56dbfgga, vxpip-hldapi03, vxkip-c5ds0001, vxkip-9txkuqgk, vxpip-xhbkkx7b, vxkep-k8p2d2rg, vxpip-sj6ks9hm, vxpip-hldapi02, vxpip-hproxp04, vxkep-d6tv6hep, vxkep-slmid01, sxpip-zf7ukryc, vxpip-slmid03, vxpip-hcedsc02, vxkip-hcentx02, vxpip-puwsvc01, axkip-czhvj7vu, vxpep-slmid01, vxpip-xnekzayn, vxpip-jkhxzdvs, axkip-cvpk643p, sxpip-mhh5s6dq, vxpip-78jwwmgg, vxkip-htnsec04, axkip-clpac1en, lx-hssasmt-p04k, vxkip-3h86kh7e, vxpip-6er6gb7e, vxpip-htphgw01, vxpep-ynmx3fda, vxpip-y972xq5j, vxkep-ecapas21, vxkip-xqtnrdhn, vxkip-dnuk2vtt, vxkep-ecapas24, vxpip-r8b6mq2p, vx-eatkntn-p02k, sxpip-4nmwz82d, vxpip-ewkret06, axkip-cj5s7fae, sxpip-6u9hjpaw, vxpip-hmrspf05, vxpip-3u77dkcc, vxpip-pdcmkr02, vxpip-jnfm6ehw, sxpip-vw2zcvdq, vxpip-6ppcsaaq, axkip-cqgagu03, vxpip-jrejbg8k, sxpip-vbycy5va, vxkip-hproxp02, vxpip-9jn6rf3j, vxpip-hcentr02, axpip-ck6f5ckn, vxkip-hmrspf03, axkip-c431t01c, vxpip-hcentr01, vxkip-tus7uk7b, vxkip-74bwsyjq, vxkep-ecapas07, axkip-csszoo2y, axkip-chdpbid2, axpip-cn8pic7b, vxpip-htsmmt01, vxpip-5vu6jzbg, sxkip-np8yacwm, vxpip-wzf6jmcb, sxpip-37cdez6j, vxpip-hmrspf04, vxpep-qvrkuzzg, vxpip-ewkret08, vxkip-nrd7sjug, vxpip-ze3hdrdu, axkip-ct65pwp5, vxkep-ecapas06, vxkip-c7di0001, vx-amsftp-p03k, vxpip-hngper01, sxpip-6x5fkakb, axkip-c7i3ymff, vxpip-hspdbx01, lx-hssklm0-p02p, vxpip-5657squm, vxkep-slmid05, vxpip-hradus02, vxkip-hldapi04, sxkip-uphpctah, vxkip-hmrsds02, vxpip-9uxnw8mm, vxkip-6arkpx5a, vxpip-nv7gqmvx, vxkip-2ny2ypya, axkip-cbok948o, lx-hssascp-p09k, vxpip-k59pgf6b, vxkip-sn347ske, axkip-cbu99hbn, vxkep-gserfw03, vxkip-cimftp02, vxkip-f7j2au3e, lx-hssascp-p07k, vxrip-pshrmq04, vxpip-hmrsds04, vxpip-hldapi04, vxkip-hsphec04, axkip-czxwzgcx, vxkip-hmrsds01, vxkip-slmid05, vxpep-jgmr5kwz, vxpip-hngper09, vxkip-d4a6tkyb, vxpip-hmqadm01, vxpep-ecapws01, vxkip-sd89prxx, axkip-c39rjzqt, sxpip-k4stpptg, vxkep-ecapas15, vxkip-aagwab06, vxpep-hcentr02, sxpip-xh9et7ab, vxpip-hgpfs003, vxpip-rtzv22rz, vxpip-zh7kkdtt, vxpip-4bs8ezan, vxpip-5pnfe2yq, vxpip-hproxp03, vxkip-hmrsds03, vxpip-kbqnnkks, axkip-c5ox3h6j, vxpip-3vyk3h9s, axpip-cxqdk3p3, vxpip-47gy729q, axkip-cpw4ht44, vxkip-mwjwxrfw, vxpep-hcentr01, sxpip-3bej78ey, axkip-cxjf1wo9, vxpip-ffa9fnjd, vxkip-69jzjxdc, vxkip-hcentx03, vxpip-esaweb01, sxpip-6vjp5tvq, vxpip-dp6ed7gh, axkip-c7e4tx02, vxrip-ashwmq01, vxpip-uzs7qhdd, vxpip-z89n3sux, vxkep-ecapas20, sxpip-v7tq5n2a, vxpip-uk76jeuk, vxpip-hmrspf01, sxkip-vj4r2xup, vxpip-r768sdbg, vxpip-bwasbnen, vxpip-eiamlb02, vxpip-ka4p87jd, vxpip-hmysql01, vxkip-tsaxvs6q, vxkep-gserfw04, vxpip-hrhel001, sxkip-svbuxpfu, vxpip-tqyxwedd, vxkip-m2tcxfyu, vxpip-nkbzwf5r, sxpip-xhg25udd, vxpip-ahh7te7q, vxkip-5rfcur5z, vxpip-vec6uytn, vxpip-9qvjbnpc, vxkip-t7gh36pc, sxpip-wuyyvd7k, axkip-cut9k5r6, vxpip-bs8c7rbt, axkip-cuq892jl, vxkip-t76n3brm, lx-hssasmd-p04k, vxpip-ak3npbqv, vxkip-hevp0012, vxpip-ydxbefue, vxpip-96m56m7g, vxkip-hmrspf02, vxpip-tz7ta9xz, vxpip-yycfku5c, sxpip-tv4dumct, vxkip-23q9y6rs, vxpip-8mcqhbct, sxpip-sqs9mmba, vxkip-adqxjxhw, vxpip-vp3e66zz, vxkip-acawad01, sxpip-fhyawbqf, lx-hssklm0-p03k, vxkip-hngper08, sxpip-kms2tp9b, vxkip-9m75m6jg, vxpip-rhnjf8qu, axkip-c4s7x08h, sxpip-zxjwt3sy, vxkip-c7di0002, lxpip-hsklm01, axkip-c8d991ju, axkip-c2ehkw80, vxpip-slmid04, vxrip-pmqats14, vxpip-uxhrxcxa, vxpip-xay57b2r, sxpip-3jk5tkfk, vxpip-hcnplm02, vxpep-slmid02, vxpip-hcentr04, vxkip-x6p45enb, vxkip-hsphec06, vxpep-9ugktmry, vxkip-hsplkr06, vxpip-ewkret03, vxkip-57m9xkat, vxkip-hproxp01, sxpip-6ygz2xgk, vxpip-hhsvc001, vxkip-krksmdnx, vxpip-aytpur3d, vxpip-htpcgw01, vxpip-yhmy95ff, vxpip-hldapi01, vxkip-hngper06, vxpip-hngper08, vxkip-6tffjwda, vxkip-hsphec05, vxpip-2v74jb3u, vxpip-r6jes7fb, vxpip-hldape01, vxkip-cdibat01, vxkip-aiodpl01, sxpip-quzn8pqs, sxpip-4n4b99qn, vxpip-646467za, axkip-cg7snwep, vxkip-hngper09, vxpip-vrsqdrsj, lx-hssklm0-p04k, vxkip-hngper07, vxpip-hproxp06, vxpip-bn3tyuxk, vxpip-qpau8u6p, vxpip-hitsmu01, vxkep-ecapas08, lx-hsnetop-p01k, vxpip-hngpes03, vxrip-ashwmq03, sxpip-khr4cv5p, vxpip-yvtggwne, vxkip-b37td9qz, vxpip-htphgy02, lxpip-hmvcm01 | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | PRAVALLIKA MALEPATI | AUTHORIZE | Normal
CHG06998465 | 2026/02/06 02:00:00 | 2026/02/06 08:00:00 | Upgrade centrify agent to 6.1.1 version (Offline activity) | USRM, CF, GRS, GDS | RAPID, GRS UW Billing Terms Capture, CEDED REINSURANCE INVOICING AND BILLING SYSTEM (CRIBS), Unbundled Service Fees, AFP2PDF CONVERTER SERVICE, p188pdc, pa03kdc, pm74kdc, p843pdc, pgb5kdc, pd7ckdc, pa02kdc, pm75kdc, CentrifyDC, p841pdc | Yes | Yes, greater than an hour | Yes | Moderate | Non-Production (Non-Prod) | ENTERPRISE AGENT HEALTH MONITORING | Chiranjeevi Dandu | SCHEDULED | Normal
CHG07043311 | 2026/02/06 02:00:00 | 2026/02/06 05:00:00 | Shutdown PTA5ZFPJ database on vxpit-a5zfpjcw server for monitoring one month to plan for decommission. | GRM E¦W, GRS, GCS, GLOBAL RISK SOLUTIONS - LII APAC, INV, USRM, GDS, LIT, CF | vxpit-a5zfpjcw, LM UNIVERSAL REINSURANCE SYSTEM | Yes | Yes, less than an hour | No | Moderate | Test | ORACLE - MONGO MIDRANGE TIER 1 | Mallikarjun Reddy Pabbathi | ASSESS | Normal
CHG07075254 | 2026/02/07 22:00:00 | 2026/02/08 08:00:00 | HDOSD-44204- MSP332 - Firmware Upgrade - scheduled on 02/7/2026 10PM to 02/08/2026 8AM | USRM, GRS, GCS, GDS, CF, INV | papip-cmadwa02, papif-crtsmb01, czar, papip-creina02, papip-cmiwea01, MSP332, MSP332VIO2P, papip-cmwebw04, earl, papip-cmwcpa01, papip-cnmwba02, papip-cmwebw05, papif-cmadwa01, PAPIP-GINFDB02, papip-cmowca02, papif-cmwebw02, papif-clibta01, papip-cirpda02, papif-cmwebw07, sadlib, pje9pdc, papif-ccmpsa02, traffic, papip-cmwebw02, papif-creina01, papif-cmcssa01, papif-cmowca01, pf1epdc, papip-cmfina02, papip-crtsma01, papip-cmcssa02, papif-cmwebw03, MSP332VIO1P, exprs02, CM Claims Dashboard, ARMS Bill Scheduler, WSPR (WU), EXMAN OPMART, IWE ADS Premium, IWE Platform and UI, NMWB - NM Workbench, FAM - Financial Agreement Manager, CEDED REINSURANCE INVOICING AND BILLING SYSTEM (CRIBS), Shared Services, AFP2PDF CONVERTER SERVICE, iCase Manager, Backup Services TSM, REINSURANCE DOCUMENT LIBRARY (RDL), SSI Viewer, Medical Disability Management, eFROI - Electronic First Report Of Injury (Distribution Utility), IWE ADS Loss, Claim Overview, IWE CPS AdHoc Reporting, Loss Cost Multiplier (LCM), RISKTRAC, ExPRS Data Services, IWE Financial Drilldown (FINDD), GRS IWE LDW Published Reporting, CI - RMIS Salesforce, CEDED REINSURANCE CONTRACT SYSTEM (CRCS), Cash Flow, Automated Life Pension System (ALPS), MANUAL CLAIM ENTRY (MCE), IWE RSR and SLR, CM Claim Alerts, GRS IWE ExPRS Workload Reporting, INTAKE UTILITY, Electronic State Reporting, Coverage Verification, RAPID, Liberator | No | Yes, less than an hour | No | Moderate | Production (Prod) | LINUX SERVER TIER 1 | Imam Jafar Sadiq | AUTHORIZE | Normal
CHG07077199 | 2026/02/07 22:00:00 | 2026/02/08 08:00:00 | HDOSD-44204- MSP326 - VIO Microcode Upgrade -offline activity- scheduled on 02/7/2026 10PM to 02/08/2026 8AM | GRS, GDS, CF | pm66pdc, exprsdb04a, pgf6pdc, pgb9pdc, MSP326VIO1P, dilbert, p5c6pdc, MSP326VIO2P, muskie, pga7pdc, ph07pdc, pgf9pdc, p149pdc, CMS/Ensemble - CERC, LIBRA Front End, Medical Cost Summary, CM Claims Dashboard, Loss Control Workstation, LIBRA RATE UTILITY, WC Claims Error Browser, INTAKE UTILITY, eFROI - Electronic First Report Of Injury (Distribution Utility), ExPRS Data Services, CM Claim Alerts, Claim Overview, GRS WC CCPA Service, CI - SMART to Premium Management, Conductor WC, Authorization (WC), Medical Disability Management, LIBRA, Electronic State Reporting, CM - Bocomp Plus, Sample Master, Shared Data Services, Claim Summary, Report Management Portal, RAPID, Liberator | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | Imam Jafar Sadiq | AUTHORIZE | Normal
CHG06808021 | 2026/02/08 01:00:00 | 2026/02/08 08:00:00 | IPL SYSC and SYSD - Rename Easytrieve LOAD libraries in preparation for removal | USRM, CF, GDS, GCS, GRS, INV | ECC-SYSD | Yes | Yes, less than an hour | No | Moderate | Production (Prod) | MAINFRAME SOFTWARE | Alan Braddock | AUTHORIZE | Normal
CHG06958203 | 2026/02/08 02:00:00 | 2026/02/08 03:00:00 | PDC (A/C/D/E/G/Q) IPL on 2/8/2026 at 2AM EST -0055-Portsmouth, NH | USRM, GRS, INV, GCS, GDS, CF | MAINFRAME PLATFORM COMPUTE SERVICES | Yes, with known High Availability/HA or Redundancy - no business impact | Yes, less than an hour | No | Moderate | Production (Prod) | ISO COMPUTER OPERATIONS | Mohammed ShaikSimar | SCHEDULED | Normal
CHG06994126 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | LM Prod -HDOSD-44596- VMware Tools upgrade 13.0.5.0 | GDS, INV, GRS, GRM E¦W, CF, GCS, USRM | vmpip-hccmmp12, vmpip-hlmcl01, vmpip-6jzrxfbz, vmpip-hdsqs001, vmpip-hvipdc05, vmpip-hscdfs05, vmpip-dh9xzx3y, vmpip-eedisc04, vmpip-hsoiam01, vmpip-287qu76k, vmpip-hccmdp07, VMPIP-23VYTZVA, vmpip-hscdfs06, vmpip-hcxcce02, VMPIP-HLIUDC01, vmpip-eedisc29, vmpip-hhpdpm01, VMPIP-HLMDC048, vmpip-hcxpsh02, vmpip-hhpepa01, vmpip-hpexcl01, vmpip-hlmdc052, vmpip-apiapa01, vmpip-eedisc25, vmpip-7cfkt9hv, vmpip-9dxheaxf, VMPIP-3B7Z5YST, vmpip-hcxcce04, vmpip-hlmamm02, vmpip-eedisc27, vmpip-j8wrwbac, vmpip-3kv2se5d, vmpip-hexwit01, VMPIP-HLIUDC02, vmpip-hvats001, vmpip-hccmpr06, vmpip-hccmsu05, vmpip-hcxcce05, VMPIP-HLITDC04, VMPIP-HLMGDR02, VMPIP-HLIHDC03, VMPIP-HCXVCC36, vmpip-8jfv649r, vmpip-hlmamm01, VMPIP-HDRFCL01, vmpip-eedisc30, vmpip-hccmcn05, vmpip-j56tj7jn, vmpip-hlmad005, VMPIP-HLIBDC02, vmpip-hcxcci04, vmpip-hcxccc23, VMPIP-HMYBCK01, vmpip-hpindc04, vmpip-hliucl01, vmpip-hlmdc053, vmpip-j2b6q2vg, vmpip-agap0003, vmpip-hvenca03, vmpip-hpincl01, vmpip-hcsm0007, vmpip-hscdfs04, vmpip-hcasvc02, VMPIP-HVENCA05, vmpip-hopjmp01, vmpip-hcxccc05, vmpip-fe79x7my, VMPIP-HEXNPLM1, vmpip-eedisc26, VMPIP-HNPCA007, vmpip-hlmad006, VMPIP-HVIPDC02, vmpip-hcxcci02, vmpip-hdspmt01, vmpip-hthibk01, VMPIP-HLMDC047, vmpip-hccmcn06, vmpip-9sbaqyxy, VMPIP-HLMDC051, vmpip-hhpepa11, vmpip-j7yjmxww, vmpip-bzzc6q4h, VMPIP-HCXVCC35, VMPIP-HLMDRDC02, VMPIP-HEXNPLM2, vmpip-hlfile03, vmpip-hcxccc04, vmpip-hlmdc043, vmpip-apiapa03, vmpip-hccmmp11, vmpip-hscdfs07, vmpip-bfw3sq8a, vmpip-hcxccc03, vmpip-hlmad007, vmpip-j6vhwjkc, vmpip-3zdr3egb, vmpip-hlmamm03, VMPIP-HLIUG02, VMPIP-HKADSVR1, vmpip-hcxcci03, vmpip-9qcwfekv, vmpip-hccmcc01, vmpip-hcmapp05, VMPIP-HLITDC02, vmpip-hlmtdc10, vmpip-eedisc19, vmpip-hwins004, vmpip-hlocgdc01, vmpip-agap0004, vmpip-4cxy6dmu, vmpip-hdfsr001, vmpip-hlmdc050, vmpip-hlmwit02, vmpip-3qtjwfse, vmpip-hhpdpm03, vmpip-akw2hdgx, vmpip-hcxbld10, vmpip-djy3fjpq, vmpip-hdexcl01, vmpip-hcxccc20, vmpip-4js7nqmq, vmpip-hcxcci06, VMPIP-HLMDC042, vmpip-j3d56hcp, vmpip-eedisc31, vmpip-hccmmp10, VMPIP-HPINDC03, vmpip-hnpcl001, vmpip-apinaa02, vmpip-hpinbk02, vmpip-hcxcci01, vmpip-hcxcce03, vmpip-hccmdp05, vmpip-hlmtca04, VMPIP-HLMDC041, vmpip-hexops01, vmpip-hcxcci05, vmpip-apiapa02, VMPIP-HLMDC045, VMPIP-HCXVCC37, VMPIP-HVIPDC01, vmpip-hccmdp04, vmpip-hdspmt02, vmpip-eedisc28, vmpip-hexucm06, vmpip-hlfile04, VMPIP-HLIHDC04, vmpip-gbtcca03, vmpip-dr4a8rrr, vmpip-hscdfs08, VMPIP-HLMGT007, VMPIP-HLMGDR01, vmpip-hccmcn04, vmpip-hvssp002, vmpip-eedisc22, vmpip-eedisc34, vmpip-hcxlic19, vmpip-hcxcce01, vmpip-hvipdc03, vmpip-8xxvctxn, vmpip-hocgcl01, vmpip-hccmpr05, vmpip-hcxcci07, vmpip-htests01, vmpip-hcxcce06, vmpip-hvxrmg02, VMPIP-HCNPCL01, vmpip-hdsfin01, vmpip-hcxlic11, vmpip-hccmdp06, vmpip-gbtcca04, vmpip-95c4pcwy, vmpip-hlmdc038, vmpip-hcxpsh01, vmpip-hexsvr02, vmpip-hccmmp09, VMPIP-HLMGDC08, vmpip-hexsvr01, vmpip-hlmcrl02, vmpip-j65g9hzk, vmpip-eedisc20, vmpip-hexucm05, vmpip-eedisc17, vmpip-hhkbck01, vmpip-hkms0004, vmpip-hccmut01, VMPIP-FU8UH8RT, vmpip-fshh8u4e, vmpip-eedisc15, vmpip-apinaa01, vmpip-eedisc24, VMPIP-HLMDC044, vmpip-hlmama01, VMPIP-HLMDC049, vmpip-hvnbck01, VMPIP-HLMDC046, vmpip-hccmcl03, vmpip-hpexptmp, vmpip-hlmtca05, vmpip-hpharo11, vmpip-hccmsu04, ACTIVE DIRECTORY SERVICES, ANAPLAN CONNECT, RECOVERY MANAGER FOR ACTIVE DIRECTORY, WINS, PHAROS BEACON, Prod_Sat_9pm, CITRIX SERVICES ON-PREMISE, GS_FS_Prod_Sat_4am, Prod_Sun_8:30am, PUBLISHING FORMS DOMAIN, Prod_Sat_11pm, Prod_Sun_4am, GAP - NEAD WEB TRANSLATION SERVICE, Software Intelligence, Prod_Sun_1am, MICROSOFT ENDPOINT CONFIGURATION MANAGEMENT SERVICES (MECM), HS_DS_Prod_Sat_1am, GS PUBLISHING (OPUS), Prod_Sun_5am, GAP_Tool_SAFECO, EXCHANGE SERVICES On-Prem, WINDOWS IDENTITY MANAGEMENT SERVICES, SAFECO NAME AND ADDRESS UTILITY (NAU), VIDEO COMMUNICATIONS - VIDEO, WINDOWS OS SERVICES, VMWARE VCENTER SERVER, GRS UW Specialty Doc Gen UI, Prod_Sat_6am, HK ACTIVE DIRECTORY, MIDRANGE SERVER MAINTENANCE, ITDS OPERATIONS JUMP, CF_Finance_Prod_Sun_2am, HS_DS_Prod_Sun_1am, MICROSOFT CERTIFICATE AUTHORITY, DOCUMENT SOLUTIONS CAPTURE CAPTIVA US, GRS LIU Claim Feeds, AMCLAIMSSAFECO, LCW VDI COMPUTE ON-PREMISE, Prod_Sun_2am, HS_CTX_Prod_Sat_11pm, CAM PHOENIX, Storage Services Tools, VORMETRIC DATA SECURITY MANAGER SERVICES | Yes | Yes, less than an hour | Yes | High | Production (Prod) | WINDOWS SERVER TIER 1 | RAGHAVAN PARTHASARATHY | AUTHORIZE | Normal
CHG07059180 | 2026/02/08 02:00:00 | 2026/02/13 23:59:00 | GRSVTDPRD - HDPSD-50301 - Decommission CORP Legal application setup that got retired from Teradata | GRS, GDS | GRS Teradata Vantage AWS | No | Yes, greater than an hour | No | Low | Production (Prod) | TERADATA VANTAGE DB TIER 1 AND 2 | Srikanth Polavaram Srinivas Manohar | SCHEDULED | Normal
CHG07061292 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | Need to Decom the Physical Servers of KDC ESS Storage | GCS, USRM, GDS, INV, CF, LIT, GRS, GLOBAL RISK SOLUTIONS - LII APAC, GRM E¦W | lckip-hisspr01, USRM SAS GRID | No | Yes, less than an hour | No | Low | Development (Dev) | STORAGE AND BACKUP - RECOVERY | Kishore Mallakedi | SCHEDULED | Normal
CHG07074098 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | HDOSD-44732¦¦KDC Linux Server Patching Config Update (Online activity) | GRM E¦W, CF, USRM, GRS, GCS, GDS, INV | vxkip-hldapi01, vxkip-p7cbs001, vxkip-hsprxy03, vxkep-ecapas17, vxkep-ecapas21, vxkip-acawab02, vxkip-hsmwmq01, vxkep-gserfw03, vxkep-ecapas11, vxkip-86x4dpxy, vxkip-9m75m6jg, vxkip-pshrmq13, vxkip-cimtda01, vxkep-gserfw04, vxkip-399ttgqw, vxkep-f95cx9us, vxkip-hcentx03, vxkep-ecapws01, vxkip-5mw76tdc, vxkip-hmrspf07, vxkip-f5n4g84p, vxkep-ecapas07, vxkip-c5uw0005, vxkip-hproxp02, vxkip-mdjzv5zt, vxkip-hngper02, vxkip-c5ds0001, vxkip-hsprxy01, vxkip-krksmdnx, vxkip-pshrmq14, vxkip-cimftp01, vxkip-slmid02, vxkip-c7ca0001, vxkip-slmid04, vxkip-hnetap01, vxkip-69jzjxdc, vxkip-yahn7cjt, vxkip-hngper06, vxkip-hsphec04, vxkip-mvwxxdcr, vxkip-d9encb7f, vxkip-c5uw0001, vxkip-hldape01, vxkip-ashwmq02, vxkip-ashwmq03, vxkip-4ddt9u8z, vxkep-ecapas20, vxkip-sqgfcv2v, vxkip-hsphec03, vxkip-4d672d8s, vxkep-ecapas08, vxkip-cppdmk01, vxkip-hproxp06, vxkip-bz5rj3jn, vxkip-dnuk2vtt, vxkip-ccased01, vxkip-hmrspf08, vxkip-c7fn0001, vxkep-ecapas25, vxkip-yks6zrrg, vxkep-ecapas09, vxkip-hldape02, vxkip-hmrsds02, vxkip-nweekuyp, vxkip-ashwmq01, vxkip-ssrvpsvg, vxkip-6swks5yj, vxkep-ecapas23, vxkip-ewkrci02, vxkip-j338xdqp, vxkip-hmrspf03, vxkip-6arkpx5a, vxkip-aagwab05, vxkip-cimbat02, vxkip-tus7uk7b, vxkip-cdba0001, vxkip-hldape04, vxkip-hngper07, vxkip-qk9c97gc, vxkip-hmqadm01, vxkip-hsphec05, vxkip-sd89prxx, vxkip-ashwab02, vxkip-hngpes03, vxkip-t76n3brm, vxkip-creins01, vxkip-slmid03, vxkip-5md2vv6w, vxkep-ecapas14, vxkip-hldapi03, vxkip-hsplkr06, vxkip-5bws2scu, vxkip-cimgg001, vxkip-hldape03, vxkep-ecapws02, vxkip-c7ca0004, vxkip-hcentr01, vxkep-ecapas10, vxkip-acawab03, vxkep-slmid04, vxkip-hmrsds01, vxkip-szvjygsh, vxkep-slmid01, vxkip-pshrmq11, vxkip-slmid01, vxkip-aagwab06, vxkip-hcentx02, vxkip-hradus01, vxkip-amfynxer, vxkip-hsplkr05, vxkip-nrh3h4cc, vxkep-ecapas18, vxkip-98vwgyad, vxkip-d8yfx2yn, vxkip-c7di0006, vxkip-x6p45enb, vxkip-ewkrci01, vxkip-c7pp0009, vxkip-b37td9qz, vxkip-hcentx01, vxkep-ecapas22, vxkep-slmid05, vxkip-htnsec02, vxkep-ecapas24, vxkip-hngper08, vxkip-3h86kh7e, vxkep-ecapas15, vxkip-hevp0012, vxkip-ashftp01, vxkip-cimftp02, vxkip-hcfscp02, vxkip-6tffjwda, vxkip-slmid05, vxkip-hproxp01, vxkip-cimftp03, vxkip-hproxp05, vxkip-fpc8udmh, vxkip-hevp0011, vxkip-rh9jzjev, vxkip-c7pp0016, vxkip-7cc8n39v, vxkip-97ka86md, vxkip-hcfscp03, vxkip-hsphec06, vxkep-z82a7b8r, vxkip-hldapi02, vxkip-7pmcvmjx, vxkip-hmrspf02, vxkip-cimadw01, vxkip-x69usv4n, vxkip-cspubw01, vxkip-c7di0001, vxkip-acawab04, vxkip-ccamp001, vxkip-hmrspf09, vxkip-ebsmes01, vxkup-hcloud21, vxkip-hmrsds03, vxkip-acmwdm01, vxkip-hldapi04, vxkip-hngper09, vxkip-hproxp03, vxkip-hsphec01, vxkip-acmwas05, vxkip-hproxp04, vxkip-63raqqez, vxkip-c7di0005, vxkip-73uvkpep, vxkip-c7pp0011, vxkip-pshrmq12, vxkip-hsphec02, vxkep-k8p2d2rg, vxkep-ecapas19, vxkip-4jj2vc3j, vxkip-f7j2au3e, vxkip-c7bl0002, vxkip-2ny2ypya, vxkip-rwtts8ba, vxkip-9txkuqgk, vxkip-aagwad01, vxkip-c7di0002, vxkip-hsprxy02, vxkip-c7ca0005, vxkip-d4a6tkyb, vxkip-ebsmes02, vxkip-bxqy9x7s, vxkep-slmid02, vxkep-ecapas16, vxkip-hmrspf01, vxkip-sn347ske, vxkip-fzc7wxvs, vxkip-57m9xkat, vxkip-22psk67b, vxkip-hngpes04, vxkip-m2tcxfyu, vxkip-acawab01, vxkip-hcfscp01, AM - First Report of Injury (FROI), ADW PREMIUM, ADW PAL LOSS, AM-DA BILLING DOMAIN ADAPTER, Linux_Prod_Week2_PatchOnlyVorm, @Work Premium Audit Workstation, GRS UW Loss Forecast Model, AM - ETM, Clipper, ADW CONTACTS, LM REINSURANCE EXTERNAL INBOUND INTERFACES, CI - CI PORTAL, CLAIMS FINANCIAL LOSS INTEGRATION (CFLI), GRS UW Driver Management, TACACS-RADIUS SERVICES, WRS FNOL - Web Routing Service and First Notice of Loss (CSRM), WEBSPHERE MQ, CI - NI Cash Remit Processor, AM - WRS REAL-TIME SERVICES & EDELIVERY, AM - CENTRAL AGENCY REPOSITORY (CAR), LCW VDE COMPUTE ON-PREMISE, SYSLOG-NG, AM - Claims DataMart (CDM), Linux_Prod_Week1_PatchOnlyVorm, AM - CLPS COMMERCIAL LINES POLICY SERVICES, Linux_Prod_Week2_PatchReboot, AM-BLS BILLING SYSTEM, ENTERPRISE INFORMATICA POWERCENTER, AM - ECLIQ OPERATIONAL DATA STORE, Middle Market Operational Reporting, ADW WC, GRS ADW CVO, Linux_Prod_Week1_PatchOnly, AM-STEPS SECURED TRANSACTION ELECTRONIC PAYMENT SYSTEM, CBS CASH REMITTANCE PROCESSOR, USRM Content Navigator, CLAIMS WC NOTIFY, GRS ADW Claims Digital Content Management (CDCM), AM-ACS AGENCY COMMISSION SYSTEM, SPLUNK ENTERPRISE, AM - CLAIMS SEARCH, CLAIM CONSOLIDATED DATA SERVICES, ZSCALER PRIVATE ACCESS, Storage Services Tools, SAF-SDM-SBI DATA MART, GRS ADW GCC, Claims Loss Operational Reporting, AM-AF ARRANGE FINANCIALS, CLAIMS DIAL, ADW EXPRS, Linux_Prod_Week4_PatchOnly, GRS ADW BLCC, PINGACCESS, VERITAS, Compensation Data Integration, Caliber, OC - MANUAL CLAIM CODING (MCC), CLAIMS INTEGRATION ADAPTER (CIA), Linux_Prod_Week1_PatchReboot, LDAP Internal Services, ADW LOCATION, NI Reporting, Managed Payments, ADW CUSTOMER CONTRACT, GRS ADW RCS, Linux_Prod_Week4_PatchOnlyVorm, LDAP EXTERNAL SERVICES, PINGFEDERATE, TOBE Cash Remittance, ELECTRONIC CUSTOMER REGISTRATION (ECR), ADW COMPLEX AND EMERGING RISK CLAIMS (CERC), USRM Content Manager, CI - DIAL2 Core Components, CI - TERADATA ACTIVE DIRECTORY SYNC PROGRAM, AM - Claims Outbound FNOL, Oracle Enterprise Manager, Linux_Prod_Week2_PatchOnly, CI - Legacy OCAS Claim Adapters, ADW PRODUCER, Linux_Prod_Week3_PatchReboot, LMP ENGINEERING WORKSTATION, Linux_Prod_Week3_PatchOnlyVorm, Property/EB Reporting, AM-SPS DIAL, LM UNIVERSAL REINSURANCE SYSTEM, BUSINESS SERVICES - ESP, ADW REFERENCE, NESSUS SERVICES, eCLIQ 2.0, CENTRIFY SERVICES, TOBE Collections Cash Remittance, HS DATADOG, CENTRIFY LDAP PROXY, OC - AGENCY INFORMATION ARCH. | No | Yes, less than an hour | No | Moderate | Production (Prod) | LINUX SERVER TIER 1 | Rajiv Gandhi | AUTHORIZE | Normal
CHG07074234 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | Need to reboot odprod on 08/02/2026 2AM to 8AM EST | CF, GDS, GRS, USRM | odprod, REINSURANCE DOCUMENT LIBRARY (RDL), ARMS Bill Scheduler, GRS OnDemand Request Daemon, VIA PAL Claims Correspondence, GRS OnDemand Notification Daemon, Managed Payments, Clipper | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | Satheeshkumar Vaithilingam | AUTHORIZE | Normal
CHG07081313 | 2026/02/08 02:00:00 | 2026/02/08 05:00:00 | Permit access limited to LM Networks for olympus.libertymutual.com and prod2.olympus.libertymutual.com | USRM, GDS, GRS | AKAMAI, ES Buscador Nexus | No | Yes, less than an hour | No | Moderate | Production (Prod) | WAF AND CONTENT DELIVERY TIER 2 | Prasanth Katakam | AUTHORIZE | Normal
CHG06997458 | 2026/02/10 02:00:00 | 2026/02/10 08:00:00 | Upgrade centrify agent to 6.1.1 version (Offline activity) | USRM, GDS, CF, GRS | Liberator, Clipper, Storage Services Tools, MANUAL CLAIM ENTRY (MCE), REINSURANCE DOCUMENT LIBRARY (RDL), CEDED REINSURANCE CONTRACT SYSTEM (CRCS), CEDED REINSURANCE INVOICING AND BILLING SYSTEM (CRIBS), pakid-cmwebw05, papid-hhdoat01, papit-hvormaix, papit-cclp1p01, CentrifyDC, pakit-cmwebw03 | Yes | Yes, greater than an hour | Yes | High | Non-Production (Non-Prod) | ENTERPRISE AGENT HEALTH MONITORING | Chiranjeevi Dandu | SCHEDULED | Normal
CHG06945303 | 2026/02/15 | 2026/02/15 08:45:00 | RDC - SYSA/SYSB - Upgrade SAS to V9.4TS1M8 | GRS, INV, CF, GDS, GCS, USRM | RDC-SYSA, RDC-SYSB, SAS 9.4, MXG 34.06 | No | Yes, less than an hour | Yes | Moderate | Production (Prod) | MAINFRAME SOFTWARE | VIJAY KOWSIK | NEW | Normal
CHG07085559 | 2026/02/15 06:00:00 | 2026/02/15 11:00:00 | Yearly Refresh of the Mainframe Certificates for Entrust Distrusted certificates in production OCG PROD01 | GCS, INV, GDS, USRM, CF, GRS | MAINFRAME PLATFORM COMPUTE SERVICES | No | Yes, less than an hour | Yes | Moderate | Production (Prod) | MAINFRAME SOFTWARE | Fernando Rodriguez | NEW | Normal
CHG07085558 | 2026/02/15 07:00:00 | 2026/02/15 13:00:00 | IPL SYST- Adding CICSV6.2 libraries to APF and LPA. Mount CICSV6.2 ZFS to Z/OS UNIX SERVICES | GRS, GCS, GDS, CF, INV, USRM | AM-SYST |  |  |  | Low | Development (Dev) | MAINFRAME SOFTWARE | Kimberly Bortle | NEW | Normal

## Sheet2
Change Number | Planned Start Date & Time | Planned End Date & Time | Short Description | Business Units Impacted | Change Related CIs | Outage or Reboot Associated? | Can be Backed Out? | Other Market Validation Required? | Risk | Environment | Assigned Group Name | Full Name | Change State | Type
CHG06789519 | 2026/02/04 10:00:00 | 2026/02/06 22:00:00 | ESP to Stonebranch Migration for ESP event, PRODCONT | GCS, INV, USRM, GDS, CF, GRS | Stonebranch Workload Automation, MAINFRAME PLATFORM COMPUTE SERVICES | No | Yes, less than an hour | Yes | High | Production (Prod) | STONEBRANCH MIGRATION TEAM | Andrew Baldwin | SCHEDULED | Normal
CHG07038415 | 2026/02/05 19:00:00 | 2026/02/08 08:00:00 | Effort id # HDOSD-12886:LM Prod PATCH & REBOOT- Jan-2026-Week-1 | INV, GCS, CF, GRS, LIT, GLOBAL RISK SOLUTIONS - LII APAC, USRM, GDS, GRM E¦W | AM - REGIONAL AGENCY MANAGEMENT AND PLANNING (RAMP), OC - AGENCY INFORMATION ARCH., Liberator, AM-SPS DIAL, AM - WRS REAL-TIME SERVICES & EDELIVERY, Clipper, AM - CENTRAL AGENCY REPOSITORY (CAR), CI - CI PORTAL, Storage Services Tools, ENTERPRISE VULN MGMT. AUTOMATION SERVICES, Splunk SIEM, USCM FIN BATCH MIDRANGE, PUBLISHING FORMS DOMAIN, AM-AF ARRANGE FINANCIALS, Middle Market Operational Reporting, LM UNIVERSAL REINSURANCE SYSTEM, CI CLEARANCE, HS DATADOG, CM AUTO ID, ARMS Bill Scheduler, TOBE Collections Cash Remittance, CAR WEB SERVICES, ENTERPRISE INFORMATICA OPERATIONAL INSIGHTS (IOI), TRACS, CF SAP ROUTER, LDAP Internal Services, RSA TWO-FACTOR SERVICES, ADW CUSTOMER CONTRACT, CSOC FORENSICS STEP FUNCTION READ, GIS SECURITY APPS JBOSS STACK, Deploy Ops Utilities, Linux_Prod_Week1_PatchReboot, CENTRIFY LDAP PROXY, ALMS, MYSQL SHARED DBAAS, CM - Bocomp Plus, CBS - CHOICE BILLING SYSTEM, IMPERVA SECURESPHERE, TOBE Cash Remittance, GRMUS DATAPOWER - BACKUP, RAMP WEB SERVICES, AM-BLS BILLING SYSTEM, CLAIM CONSOLIDATED DATA SERVICES, NMWB - NM Workbench, ONESTOP UTILITIES, SAF - PEM (PROPERTY EXPERIENCE MART), WINDOWS AION RULES SERVICE, AM-RAMCAR, PCI DataPower, CENTRIFY SERVICES, SOC SIEM, Compass, SAF - HFS (HOME FREQUENCY AND SEVERITY), UNIX IDENTITY MANAGEMENT SERVICES, Linux_Prod_Week1_PatchOnly, Caliber, CI - Pool Reporting, WEBSPHERE MQ, PIDA, PINGFEDERATE, WATSON TNG, ENTERPRISE INFORMATICA POWERCENTER, VIA PAL Claims Correspondence, TACACS-RADIUS SERVICES, Linux_Prod_Week4_PatchOnly, LCW VDE COMPUTE ON-PREMISE, Publishing Print Services, SAF - AFS (AUTO FREQUNCY AND SEVERITY), CBS CASH REMITTANCE PROCESSOR, GRM GPFS SAS INFORMATICA, SYSLOG-NG, LDAP EXTERNAL SERVICES, CLAIMS FINANCIAL LOSS INTEGRATION (CFLI), AGENCY DATA SERVICES BATCH, CLAIMS DETAIL SERVICE SOE, CONVERGENCE GUI, AM-ACS AGENCY COMMISSION SYSTEM, SAF - PLA, ELECTRONIC CUSTOMER REGISTRATION (ECR), SPACEWALK, SPLUNK ENTERPRISE, DATABASE ID MAINTENANCE, MASTER PARTY INQUIRY SERVICE, MIDRANGE SERVER MAINTENANCE, DbID (Database Inventory), PI AGENCY DOWNLOAD PREFERENCE MANAGEMENT, Backup Services TSM, BigID, ENTERPRISE INFORMATICA TEST DATA MANAGEMENT (TDM), NETWORK ADMINISTRATION TOOLS, @Work Premium Audit Workstation, PINGACCESS, VIA PAL ClaimCenter, CI - DIAL2 Core Components, AM-DA BILLING DOMAIN ADAPTER, TRIPWIRE, NESSUS SERVICES, Legal Data Platform, ZSCALER PRIVATE ACCESS, APPLICATION CENTRIC INFRASTRUCTURE, MAINVIEW CONSOLE MANAGEMENT, Linux_Prod_Week2_PatchOnly, BILLS, VORMETRIC DATA SECURITY MANAGER SERVICES, vxpip-mm6eczxe, vxpip-u4pra8xh, vxpip-kanteruw, vxpip-586sazdx, axkip-cqdpmvv3, vxpip-hldape03, vxpip-56ydfadv, vxpip-hcentx03, vxpip-a5j5ph7s, vxpip-nu5wdnnz, sxpip-znjpdnqx, vxkip-aagwab05, vxkip-hsmwmq01, vxpip-hcedsc01, vxpip-hcentx01, patch, vxkip-hsphec01, vxpip-3r3ejgtu, vxpip-vtu7fksp, vxpip-hvorm001, vxpip-vbhshx2w, vxpip-cshwmq03, vxkip-hcentr01, vxpip-ewkret07, vxpip-8x2fbkyw, vxpip-hcentx02, vxpip-x7azmd5t, vxkep-z82a7b8r, vxpip-cshwmq02, vxpip-4ycszv8c, vxpip-slmid05, vxpip-rq6gndaj, vxkip-6swks5yj, sxpip-u5prhnwj, sxpip-yp4xhqbh, vxpip-nystz7va, vxpip-9nwf58qc, vxpep-kx37ugws, vxpip-mhqndeph, vxpip-hproxp01, sxpip-a3vvr9kq, axkip-cngdk4ob, vxpip-w3qpqftr, sxpip-zumhhxpp, vxkip-qk9c97gc, vxpip-ewkret05, vxpip-hsphec01, vxpip-hcnplm01, vxkup-ppcidp01, vxkip-4d672d8s, vxpep-slmid04, vxkep-ecapas16, sxpip-4vns9ksg, vxpip-3fzbakrw, sxpip-9pqzmy3y, vxpip-hngpes01, vxkip-bxqy9x7s, sxkip-wjfw27cp, vxpip-hmrsds01, vxsip-hnetop01, vxpip-h5tpc002, vxpip-pshrmq24, vxkep-slmid04, lxpip-hsecop01, vxpip-np9wnqbn, vxkip-7ftj58kq, vxkip-4ddt9u8z, axkip-cr63ws1x, vxpip-hproxp02, vxpip-ewkret04, sxpip-wwhn8bpv, vxpip-hsphec07, sxpip-bbasnqww, vxpup-ppcidp01, vxpip-wskrbt6e, axkip-cu6njgyh, vxkip-86x4dpxy, sxpip-y8xvbr5g, vxkip-hproxp04, vx-eatkntn-p02p, axkip-ck5cc4v2, axkip-cmojgpz3, vxkep-ecapas23, vxpip-r8btnm9u, vxkep-ecapas02, vxkip-hmrspf07, sxpip-vu2af9yr, vxpip-htphgy01, vxpip-hngper02, vxpip-cshwmq01, vxkip-ashwmq01, vxpep-ecapas03, vxpep-qs5c43ry, vxkip-hmrspf08, axkip-c0au2yni, vxkip-hldapi02, axpip-cnjpucge, vxpip-esaapp02, vxpip-xqec86kb, vxpip-hngper04, sxpip-w56xtwwb, vxkep-ecapas22, vxpip-ppmfin02, axkip-c71adu7p, vxkip-hngpes04, vxkep-ecapas11, axkip-ce1qhjle, vxpip-uvghdj8s, vxpip-fg9rfs6e, vxpip-56dbfgga, vxpip-hldapi03, vxkip-c5ds0001, vxkip-9txkuqgk, vxpip-xhbkkx7b, vxkep-k8p2d2rg, vxpip-sj6ks9hm, vxpip-hldapi02, vxpip-hproxp04, vxkep-d6tv6hep, vxkep-slmid01, sxpip-zf7ukryc, vxpip-slmid03, vxpip-hcedsc02, vxkip-hcentx02, vxpip-puwsvc01, axkip-czhvj7vu, vxpep-slmid01, vxpip-xnekzayn, vxpip-jkhxzdvs, axkip-cvpk643p, sxpip-mhh5s6dq, vxpip-78jwwmgg, vxkip-htnsec04, axkip-clpac1en, lx-hssasmt-p04k, vxkip-3h86kh7e, vxpip-6er6gb7e, vxpip-htphgw01, vxpep-ynmx3fda, vxpip-y972xq5j, vxkep-ecapas21, vxkip-xqtnrdhn, vxkip-dnuk2vtt, vxkep-ecapas24, vxpip-r8b6mq2p, vx-eatkntn-p02k, sxpip-4nmwz82d, vxpip-ewkret06, axkip-cj5s7fae, sxpip-6u9hjpaw, vxpip-hmrspf05, vxpip-3u77dkcc, vxpip-pdcmkr02, vxpip-jnfm6ehw, sxpip-vw2zcvdq, vxpip-6ppcsaaq, axkip-cqgagu03, vxpip-jrejbg8k, sxpip-vbycy5va, vxkip-hproxp02, vxpip-9jn6rf3j, vxpip-hcentr02, axpip-ck6f5ckn, vxkip-hmrspf03, axkip-c431t01c, vxpip-hcentr01, vxkip-tus7uk7b, vxkip-74bwsyjq, vxkep-ecapas07, axkip-csszoo2y, axkip-chdpbid2, axpip-cn8pic7b, vxpip-htsmmt01, vxpip-5vu6jzbg, sxkip-np8yacwm, vxpip-wzf6jmcb, sxpip-37cdez6j, vxpip-hmrspf04, vxpep-qvrkuzzg, vxpip-ewkret08, vxkip-nrd7sjug, vxpip-ze3hdrdu, axkip-ct65pwp5, vxkep-ecapas06, vxkip-c7di0001, vx-amsftp-p03k, vxpip-hngper01, sxpip-6x5fkakb, axkip-c7i3ymff, vxpip-hspdbx01, lx-hssklm0-p02p, vxpip-5657squm, vxkep-slmid05, vxpip-hradus02, vxkip-hldapi04, sxkip-uphpctah, vxkip-hmrsds02, vxpip-9uxnw8mm, vxkip-6arkpx5a, vxpip-nv7gqmvx, vxkip-2ny2ypya, axkip-cbok948o, lx-hssascp-p09k, vxpip-k59pgf6b, vxkip-sn347ske, axkip-cbu99hbn, vxkep-gserfw03, vxkip-cimftp02, vxkip-f7j2au3e, lx-hssascp-p07k, vxrip-pshrmq04, vxpip-hmrsds04, vxpip-hldapi04, vxkip-hsphec04, axkip-czxwzgcx, vxkip-hmrsds01, vxkip-slmid05, vxpep-jgmr5kwz, vxpip-hngper09, vxkip-d4a6tkyb, vxpip-hmqadm01, vxpep-ecapws01, vxkip-sd89prxx, axkip-c39rjzqt, sxpip-k4stpptg, vxkep-ecapas15, vxkip-aagwab06, vxpep-hcentr02, sxpip-xh9et7ab, vxpip-hgpfs003, vxpip-rtzv22rz, vxpip-zh7kkdtt, vxpip-4bs8ezan, vxpip-5pnfe2yq, vxpip-hproxp03, vxkip-hmrsds03, vxpip-kbqnnkks, axkip-c5ox3h6j, vxpip-3vyk3h9s, axpip-cxqdk3p3, vxpip-47gy729q, axkip-cpw4ht44, vxkip-mwjwxrfw, vxpep-hcentr01, sxpip-3bej78ey, axkip-cxjf1wo9, vxpip-ffa9fnjd, vxkip-69jzjxdc, vxkip-hcentx03, vxpip-esaweb01, sxpip-6vjp5tvq, vxpip-dp6ed7gh, axkip-c7e4tx02, vxrip-ashwmq01, vxpip-uzs7qhdd, vxpip-z89n3sux, vxkep-ecapas20, sxpip-v7tq5n2a, vxpip-uk76jeuk, vxpip-hmrspf01, sxkip-vj4r2xup, vxpip-r768sdbg, vxpip-bwasbnen, vxpip-eiamlb02, vxpip-ka4p87jd, vxpip-hmysql01, vxkip-tsaxvs6q, vxkep-gserfw04, vxpip-hrhel001, sxkip-svbuxpfu, vxpip-tqyxwedd, vxkip-m2tcxfyu, vxpip-nkbzwf5r, sxpip-xhg25udd, vxpip-ahh7te7q, vxkip-5rfcur5z, vxpip-vec6uytn, vxpip-9qvjbnpc, vxkip-t7gh36pc, sxpip-wuyyvd7k, axkip-cut9k5r6, vxpip-bs8c7rbt, axkip-cuq892jl, vxkip-t76n3brm, lx-hssasmd-p04k, vxpip-ak3npbqv, vxkip-hevp0012, vxpip-ydxbefue, vxpip-96m56m7g, vxkip-hmrspf02, vxpip-tz7ta9xz, vxpip-yycfku5c, sxpip-tv4dumct, vxkip-23q9y6rs, vxpip-8mcqhbct, sxpip-sqs9mmba, vxkip-adqxjxhw, vxpip-vp3e66zz, vxkip-acawad01, sxpip-fhyawbqf, lx-hssklm0-p03k, vxkip-hngper08, sxpip-kms2tp9b, vxkip-9m75m6jg, vxpip-rhnjf8qu, axkip-c4s7x08h, sxpip-zxjwt3sy, vxkip-c7di0002, lxpip-hsklm01, axkip-c8d991ju, axkip-c2ehkw80, vxpip-slmid04, vxrip-pmqats14, vxpip-uxhrxcxa, vxpip-xay57b2r, sxpip-3jk5tkfk, vxpip-hcnplm02, vxpep-slmid02, vxpip-hcentr04, vxkip-x6p45enb, vxkip-hsphec06, vxpep-9ugktmry, vxkip-hsplkr06, vxpip-ewkret03, vxkip-57m9xkat, vxkip-hproxp01, sxpip-6ygz2xgk, vxpip-hhsvc001, vxkip-krksmdnx, vxpip-aytpur3d, vxpip-htpcgw01, vxpip-yhmy95ff, vxpip-hldapi01, vxkip-hngper06, vxpip-hngper08, vxkip-6tffjwda, vxkip-hsphec05, vxpip-2v74jb3u, vxpip-r6jes7fb, vxpip-hldape01, vxkip-cdibat01, vxkip-aiodpl01, sxpip-quzn8pqs, sxpip-4n4b99qn, vxpip-646467za, axkip-cg7snwep, vxkip-hngper09, vxpip-vrsqdrsj, lx-hssklm0-p04k, vxkip-hngper07, vxpip-hproxp06, vxpip-bn3tyuxk, vxpip-qpau8u6p, vxpip-hitsmu01, vxkep-ecapas08, lx-hsnetop-p01k, vxpip-hngpes03, vxrip-ashwmq03, sxpip-khr4cv5p, vxpip-yvtggwne, vxkip-b37td9qz, vxpip-htphgy02, lxpip-hmvcm01 | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | PRAVALLIKA MALEPATI | AUTHORIZE | Normal
CHG07075254 | 2026/02/07 22:00:00 | 2026/02/08 08:00:00 | HDOSD-44204- MSP332 - Firmware Upgrade - scheduled on 02/7/2026 10PM to 02/08/2026 8AM | USRM, GRS, GCS, GDS, CF, INV | papip-cmadwa02, papif-crtsmb01, czar, papip-creina02, papip-cmiwea01, MSP332, MSP332VIO2P, papip-cmwebw04, earl, papip-cmwcpa01, papip-cnmwba02, papip-cmwebw05, papif-cmadwa01, PAPIP-GINFDB02, papip-cmowca02, papif-cmwebw02, papif-clibta01, papip-cirpda02, papif-cmwebw07, sadlib, pje9pdc, papif-ccmpsa02, traffic, papip-cmwebw02, papif-creina01, papif-cmcssa01, papif-cmowca01, pf1epdc, papip-cmfina02, papip-crtsma01, papip-cmcssa02, papif-cmwebw03, MSP332VIO1P, exprs02, CM Claims Dashboard, ARMS Bill Scheduler, WSPR (WU), EXMAN OPMART, IWE ADS Premium, IWE Platform and UI, NMWB - NM Workbench, FAM - Financial Agreement Manager, CEDED REINSURANCE INVOICING AND BILLING SYSTEM (CRIBS), Shared Services, AFP2PDF CONVERTER SERVICE, iCase Manager, Backup Services TSM, REINSURANCE DOCUMENT LIBRARY (RDL), SSI Viewer, Medical Disability Management, eFROI - Electronic First Report Of Injury (Distribution Utility), IWE ADS Loss, Claim Overview, IWE CPS AdHoc Reporting, Loss Cost Multiplier (LCM), RISKTRAC, ExPRS Data Services, IWE Financial Drilldown (FINDD), GRS IWE LDW Published Reporting, CI - RMIS Salesforce, CEDED REINSURANCE CONTRACT SYSTEM (CRCS), Cash Flow, Automated Life Pension System (ALPS), MANUAL CLAIM ENTRY (MCE), IWE RSR and SLR, CM Claim Alerts, GRS IWE ExPRS Workload Reporting, INTAKE UTILITY, Electronic State Reporting, Coverage Verification, RAPID, Liberator | No | Yes, less than an hour | No | Moderate | Production (Prod) | LINUX SERVER TIER 1 | Imam Jafar Sadiq | AUTHORIZE | Normal
CHG07077199 | 2026/02/07 22:00:00 | 2026/02/08 08:00:00 | HDOSD-44204- MSP326 - VIO Microcode Upgrade -offline activity- scheduled on 02/7/2026 10PM to 02/08/2026 8AM | GRS, GDS, CF | pm66pdc, exprsdb04a, pgf6pdc, pgb9pdc, MSP326VIO1P, dilbert, p5c6pdc, MSP326VIO2P, muskie, pga7pdc, ph07pdc, pgf9pdc, p149pdc, CMS/Ensemble - CERC, LIBRA Front End, Medical Cost Summary, CM Claims Dashboard, Loss Control Workstation, LIBRA RATE UTILITY, WC Claims Error Browser, INTAKE UTILITY, eFROI - Electronic First Report Of Injury (Distribution Utility), ExPRS Data Services, CM Claim Alerts, Claim Overview, GRS WC CCPA Service, CI - SMART to Premium Management, Conductor WC, Authorization (WC), Medical Disability Management, LIBRA, Electronic State Reporting, CM - Bocomp Plus, Sample Master, Shared Data Services, Claim Summary, Report Management Portal, RAPID, Liberator | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | Imam Jafar Sadiq | AUTHORIZE | Normal
CHG06808021 | 2026/02/08 01:00:00 | 2026/02/08 08:00:00 | IPL SYSC and SYSD - Rename Easytrieve LOAD libraries in preparation for removal | USRM, CF, GDS, GCS, GRS, INV | ECC-SYSD | Yes | Yes, less than an hour | No | Moderate | Production (Prod) | MAINFRAME SOFTWARE | Alan Braddock | AUTHORIZE | Normal
CHG06958203 | 2026/02/08 02:00:00 | 2026/02/08 03:00:00 | PDC (A/C/D/E/G/Q) IPL on 2/8/2026 at 2AM EST -0055-Portsmouth, NH | USRM, GRS, INV, GCS, GDS, CF | MAINFRAME PLATFORM COMPUTE SERVICES | Yes, with known High Availability/HA or Redundancy - no business impact | Yes, less than an hour | No | Moderate | Production (Prod) | ISO COMPUTER OPERATIONS | Mohammed ShaikSimar | SCHEDULED | Normal
CHG06994126 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | LM Prod -HDOSD-44596- VMware Tools upgrade 13.0.5.0 | GDS, INV, GRS, GRM E¦W, CF, GCS, USRM | vmpip-hccmmp12, vmpip-hlmcl01, vmpip-6jzrxfbz, vmpip-hdsqs001, vmpip-hvipdc05, vmpip-hscdfs05, vmpip-dh9xzx3y, vmpip-eedisc04, vmpip-hsoiam01, vmpip-287qu76k, vmpip-hccmdp07, VMPIP-23VYTZVA, vmpip-hscdfs06, vmpip-hcxcce02, VMPIP-HLIUDC01, vmpip-eedisc29, vmpip-hhpdpm01, VMPIP-HLMDC048, vmpip-hcxpsh02, vmpip-hhpepa01, vmpip-hpexcl01, vmpip-hlmdc052, vmpip-apiapa01, vmpip-eedisc25, vmpip-7cfkt9hv, vmpip-9dxheaxf, VMPIP-3B7Z5YST, vmpip-hcxcce04, vmpip-hlmamm02, vmpip-eedisc27, vmpip-j8wrwbac, vmpip-3kv2se5d, vmpip-hexwit01, VMPIP-HLIUDC02, vmpip-hvats001, vmpip-hccmpr06, vmpip-hccmsu05, vmpip-hcxcce05, VMPIP-HLITDC04, VMPIP-HLMGDR02, VMPIP-HLIHDC03, VMPIP-HCXVCC36, vmpip-8jfv649r, vmpip-hlmamm01, VMPIP-HDRFCL01, vmpip-eedisc30, vmpip-hccmcn05, vmpip-j56tj7jn, vmpip-hlmad005, VMPIP-HLIBDC02, vmpip-hcxcci04, vmpip-hcxccc23, VMPIP-HMYBCK01, vmpip-hpindc04, vmpip-hliucl01, vmpip-hlmdc053, vmpip-j2b6q2vg, vmpip-agap0003, vmpip-hvenca03, vmpip-hpincl01, vmpip-hcsm0007, vmpip-hscdfs04, vmpip-hcasvc02, VMPIP-HVENCA05, vmpip-hopjmp01, vmpip-hcxccc05, vmpip-fe79x7my, VMPIP-HEXNPLM1, vmpip-eedisc26, VMPIP-HNPCA007, vmpip-hlmad006, VMPIP-HVIPDC02, vmpip-hcxcci02, vmpip-hdspmt01, vmpip-hthibk01, VMPIP-HLMDC047, vmpip-hccmcn06, vmpip-9sbaqyxy, VMPIP-HLMDC051, vmpip-hhpepa11, vmpip-j7yjmxww, vmpip-bzzc6q4h, VMPIP-HCXVCC35, VMPIP-HLMDRDC02, VMPIP-HEXNPLM2, vmpip-hlfile03, vmpip-hcxccc04, vmpip-hlmdc043, vmpip-apiapa03, vmpip-hccmmp11, vmpip-hscdfs07, vmpip-bfw3sq8a, vmpip-hcxccc03, vmpip-hlmad007, vmpip-j6vhwjkc, vmpip-3zdr3egb, vmpip-hlmamm03, VMPIP-HLIUG02, VMPIP-HKADSVR1, vmpip-hcxcci03, vmpip-9qcwfekv, vmpip-hccmcc01, vmpip-hcmapp05, VMPIP-HLITDC02, vmpip-hlmtdc10, vmpip-eedisc19, vmpip-hwins004, vmpip-hlocgdc01, vmpip-agap0004, vmpip-4cxy6dmu, vmpip-hdfsr001, vmpip-hlmdc050, vmpip-hlmwit02, vmpip-3qtjwfse, vmpip-hhpdpm03, vmpip-akw2hdgx, vmpip-hcxbld10, vmpip-djy3fjpq, vmpip-hdexcl01, vmpip-hcxccc20, vmpip-4js7nqmq, vmpip-hcxcci06, VMPIP-HLMDC042, vmpip-j3d56hcp, vmpip-eedisc31, vmpip-hccmmp10, VMPIP-HPINDC03, vmpip-hnpcl001, vmpip-apinaa02, vmpip-hpinbk02, vmpip-hcxcci01, vmpip-hcxcce03, vmpip-hccmdp05, vmpip-hlmtca04, VMPIP-HLMDC041, vmpip-hexops01, vmpip-hcxcci05, vmpip-apiapa02, VMPIP-HLMDC045, VMPIP-HCXVCC37, VMPIP-HVIPDC01, vmpip-hccmdp04, vmpip-hdspmt02, vmpip-eedisc28, vmpip-hexucm06, vmpip-hlfile04, VMPIP-HLIHDC04, vmpip-gbtcca03, vmpip-dr4a8rrr, vmpip-hscdfs08, VMPIP-HLMGT007, VMPIP-HLMGDR01, vmpip-hccmcn04, vmpip-hvssp002, vmpip-eedisc22, vmpip-eedisc34, vmpip-hcxlic19, vmpip-hcxcce01, vmpip-hvipdc03, vmpip-8xxvctxn, vmpip-hocgcl01, vmpip-hccmpr05, vmpip-hcxcci07, vmpip-htests01, vmpip-hcxcce06, vmpip-hvxrmg02, VMPIP-HCNPCL01, vmpip-hdsfin01, vmpip-hcxlic11, vmpip-hccmdp06, vmpip-gbtcca04, vmpip-95c4pcwy, vmpip-hlmdc038, vmpip-hcxpsh01, vmpip-hexsvr02, vmpip-hccmmp09, VMPIP-HLMGDC08, vmpip-hexsvr01, vmpip-hlmcrl02, vmpip-j65g9hzk, vmpip-eedisc20, vmpip-hexucm05, vmpip-eedisc17, vmpip-hhkbck01, vmpip-hkms0004, vmpip-hccmut01, VMPIP-FU8UH8RT, vmpip-fshh8u4e, vmpip-eedisc15, vmpip-apinaa01, vmpip-eedisc24, VMPIP-HLMDC044, vmpip-hlmama01, VMPIP-HLMDC049, vmpip-hvnbck01, VMPIP-HLMDC046, vmpip-hccmcl03, vmpip-hpexptmp, vmpip-hlmtca05, vmpip-hpharo11, vmpip-hccmsu04, ACTIVE DIRECTORY SERVICES, ANAPLAN CONNECT, RECOVERY MANAGER FOR ACTIVE DIRECTORY, WINS, PHAROS BEACON, Prod_Sat_9pm, CITRIX SERVICES ON-PREMISE, GS_FS_Prod_Sat_4am, Prod_Sun_8:30am, PUBLISHING FORMS DOMAIN, Prod_Sat_11pm, Prod_Sun_4am, GAP - NEAD WEB TRANSLATION SERVICE, Software Intelligence, Prod_Sun_1am, MICROSOFT ENDPOINT CONFIGURATION MANAGEMENT SERVICES (MECM), HS_DS_Prod_Sat_1am, GS PUBLISHING (OPUS), Prod_Sun_5am, GAP_Tool_SAFECO, EXCHANGE SERVICES On-Prem, WINDOWS IDENTITY MANAGEMENT SERVICES, SAFECO NAME AND ADDRESS UTILITY (NAU), VIDEO COMMUNICATIONS - VIDEO, WINDOWS OS SERVICES, VMWARE VCENTER SERVER, GRS UW Specialty Doc Gen UI, Prod_Sat_6am, HK ACTIVE DIRECTORY, MIDRANGE SERVER MAINTENANCE, ITDS OPERATIONS JUMP, CF_Finance_Prod_Sun_2am, HS_DS_Prod_Sun_1am, MICROSOFT CERTIFICATE AUTHORITY, DOCUMENT SOLUTIONS CAPTURE CAPTIVA US, GRS LIU Claim Feeds, AMCLAIMSSAFECO, LCW VDI COMPUTE ON-PREMISE, Prod_Sun_2am, HS_CTX_Prod_Sat_11pm, CAM PHOENIX, Storage Services Tools, VORMETRIC DATA SECURITY MANAGER SERVICES | Yes | Yes, less than an hour | Yes | High | Production (Prod) | WINDOWS SERVER TIER 1 | RAGHAVAN PARTHASARATHY | AUTHORIZE | Normal
CHG07059180 | 2026/02/08 02:00:00 | 2026/02/13 23:59:00 | GRSVTDPRD - HDPSD-50301 - Decommission CORP Legal application setup that got retired from Teradata | GRS, GDS | GRS Teradata Vantage AWS | No | Yes, greater than an hour | No | Low | Production (Prod) | TERADATA VANTAGE DB TIER 1 AND 2 | Srikanth Polavaram Srinivas Manohar | SCHEDULED | Normal
CHG07074098 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | HDOSD-44732¦¦KDC Linux Server Patching Config Update (Online activity) | GRM E¦W, CF, USRM, GRS, GCS, GDS, INV | vxkip-hldapi01, vxkip-p7cbs001, vxkip-hsprxy03, vxkep-ecapas17, vxkep-ecapas21, vxkip-acawab02, vxkip-hsmwmq01, vxkep-gserfw03, vxkep-ecapas11, vxkip-86x4dpxy, vxkip-9m75m6jg, vxkip-pshrmq13, vxkip-cimtda01, vxkep-gserfw04, vxkip-399ttgqw, vxkep-f95cx9us, vxkip-hcentx03, vxkep-ecapws01, vxkip-5mw76tdc, vxkip-hmrspf07, vxkip-f5n4g84p, vxkep-ecapas07, vxkip-c5uw0005, vxkip-hproxp02, vxkip-mdjzv5zt, vxkip-hngper02, vxkip-c5ds0001, vxkip-hsprxy01, vxkip-krksmdnx, vxkip-pshrmq14, vxkip-cimftp01, vxkip-slmid02, vxkip-c7ca0001, vxkip-slmid04, vxkip-hnetap01, vxkip-69jzjxdc, vxkip-yahn7cjt, vxkip-hngper06, vxkip-hsphec04, vxkip-mvwxxdcr, vxkip-d9encb7f, vxkip-c5uw0001, vxkip-hldape01, vxkip-ashwmq02, vxkip-ashwmq03, vxkip-4ddt9u8z, vxkep-ecapas20, vxkip-sqgfcv2v, vxkip-hsphec03, vxkip-4d672d8s, vxkep-ecapas08, vxkip-cppdmk01, vxkip-hproxp06, vxkip-bz5rj3jn, vxkip-dnuk2vtt, vxkip-ccased01, vxkip-hmrspf08, vxkip-c7fn0001, vxkep-ecapas25, vxkip-yks6zrrg, vxkep-ecapas09, vxkip-hldape02, vxkip-hmrsds02, vxkip-nweekuyp, vxkip-ashwmq01, vxkip-ssrvpsvg, vxkip-6swks5yj, vxkep-ecapas23, vxkip-ewkrci02, vxkip-j338xdqp, vxkip-hmrspf03, vxkip-6arkpx5a, vxkip-aagwab05, vxkip-cimbat02, vxkip-tus7uk7b, vxkip-cdba0001, vxkip-hldape04, vxkip-hngper07, vxkip-qk9c97gc, vxkip-hmqadm01, vxkip-hsphec05, vxkip-sd89prxx, vxkip-ashwab02, vxkip-hngpes03, vxkip-t76n3brm, vxkip-creins01, vxkip-slmid03, vxkip-5md2vv6w, vxkep-ecapas14, vxkip-hldapi03, vxkip-hsplkr06, vxkip-5bws2scu, vxkip-cimgg001, vxkip-hldape03, vxkep-ecapws02, vxkip-c7ca0004, vxkip-hcentr01, vxkep-ecapas10, vxkip-acawab03, vxkep-slmid04, vxkip-hmrsds01, vxkip-szvjygsh, vxkep-slmid01, vxkip-pshrmq11, vxkip-slmid01, vxkip-aagwab06, vxkip-hcentx02, vxkip-hradus01, vxkip-amfynxer, vxkip-hsplkr05, vxkip-nrh3h4cc, vxkep-ecapas18, vxkip-98vwgyad, vxkip-d8yfx2yn, vxkip-c7di0006, vxkip-x6p45enb, vxkip-ewkrci01, vxkip-c7pp0009, vxkip-b37td9qz, vxkip-hcentx01, vxkep-ecapas22, vxkep-slmid05, vxkip-htnsec02, vxkep-ecapas24, vxkip-hngper08, vxkip-3h86kh7e, vxkep-ecapas15, vxkip-hevp0012, vxkip-ashftp01, vxkip-cimftp02, vxkip-hcfscp02, vxkip-6tffjwda, vxkip-slmid05, vxkip-hproxp01, vxkip-cimftp03, vxkip-hproxp05, vxkip-fpc8udmh, vxkip-hevp0011, vxkip-rh9jzjev, vxkip-c7pp0016, vxkip-7cc8n39v, vxkip-97ka86md, vxkip-hcfscp03, vxkip-hsphec06, vxkep-z82a7b8r, vxkip-hldapi02, vxkip-7pmcvmjx, vxkip-hmrspf02, vxkip-cimadw01, vxkip-x69usv4n, vxkip-cspubw01, vxkip-c7di0001, vxkip-acawab04, vxkip-ccamp001, vxkip-hmrspf09, vxkip-ebsmes01, vxkup-hcloud21, vxkip-hmrsds03, vxkip-acmwdm01, vxkip-hldapi04, vxkip-hngper09, vxkip-hproxp03, vxkip-hsphec01, vxkip-acmwas05, vxkip-hproxp04, vxkip-63raqqez, vxkip-c7di0005, vxkip-73uvkpep, vxkip-c7pp0011, vxkip-pshrmq12, vxkip-hsphec02, vxkep-k8p2d2rg, vxkep-ecapas19, vxkip-4jj2vc3j, vxkip-f7j2au3e, vxkip-c7bl0002, vxkip-2ny2ypya, vxkip-rwtts8ba, vxkip-9txkuqgk, vxkip-aagwad01, vxkip-c7di0002, vxkip-hsprxy02, vxkip-c7ca0005, vxkip-d4a6tkyb, vxkip-ebsmes02, vxkip-bxqy9x7s, vxkep-slmid02, vxkep-ecapas16, vxkip-hmrspf01, vxkip-sn347ske, vxkip-fzc7wxvs, vxkip-57m9xkat, vxkip-22psk67b, vxkip-hngpes04, vxkip-m2tcxfyu, vxkip-acawab01, vxkip-hcfscp01, AM - First Report of Injury (FROI), ADW PREMIUM, ADW PAL LOSS, AM-DA BILLING DOMAIN ADAPTER, Linux_Prod_Week2_PatchOnlyVorm, @Work Premium Audit Workstation, GRS UW Loss Forecast Model, AM - ETM, Clipper, ADW CONTACTS, LM REINSURANCE EXTERNAL INBOUND INTERFACES, CI - CI PORTAL, CLAIMS FINANCIAL LOSS INTEGRATION (CFLI), GRS UW Driver Management, TACACS-RADIUS SERVICES, WRS FNOL - Web Routing Service and First Notice of Loss (CSRM), WEBSPHERE MQ, CI - NI Cash Remit Processor, AM - WRS REAL-TIME SERVICES & EDELIVERY, AM - CENTRAL AGENCY REPOSITORY (CAR), LCW VDE COMPUTE ON-PREMISE, SYSLOG-NG, AM - Claims DataMart (CDM), Linux_Prod_Week1_PatchOnlyVorm, AM - CLPS COMMERCIAL LINES POLICY SERVICES, Linux_Prod_Week2_PatchReboot, AM-BLS BILLING SYSTEM, ENTERPRISE INFORMATICA POWERCENTER, AM - ECLIQ OPERATIONAL DATA STORE, Middle Market Operational Reporting, ADW WC, GRS ADW CVO, Linux_Prod_Week1_PatchOnly, AM-STEPS SECURED TRANSACTION ELECTRONIC PAYMENT SYSTEM, CBS CASH REMITTANCE PROCESSOR, USRM Content Navigator, CLAIMS WC NOTIFY, GRS ADW Claims Digital Content Management (CDCM), AM-ACS AGENCY COMMISSION SYSTEM, SPLUNK ENTERPRISE, AM - CLAIMS SEARCH, CLAIM CONSOLIDATED DATA SERVICES, ZSCALER PRIVATE ACCESS, Storage Services Tools, SAF-SDM-SBI DATA MART, GRS ADW GCC, Claims Loss Operational Reporting, AM-AF ARRANGE FINANCIALS, CLAIMS DIAL, ADW EXPRS, Linux_Prod_Week4_PatchOnly, GRS ADW BLCC, PINGACCESS, VERITAS, Compensation Data Integration, Caliber, OC - MANUAL CLAIM CODING (MCC), CLAIMS INTEGRATION ADAPTER (CIA), Linux_Prod_Week1_PatchReboot, LDAP Internal Services, ADW LOCATION, NI Reporting, Managed Payments, ADW CUSTOMER CONTRACT, GRS ADW RCS, Linux_Prod_Week4_PatchOnlyVorm, LDAP EXTERNAL SERVICES, PINGFEDERATE, TOBE Cash Remittance, ELECTRONIC CUSTOMER REGISTRATION (ECR), ADW COMPLEX AND EMERGING RISK CLAIMS (CERC), USRM Content Manager, CI - DIAL2 Core Components, CI - TERADATA ACTIVE DIRECTORY SYNC PROGRAM, AM - Claims Outbound FNOL, Oracle Enterprise Manager, Linux_Prod_Week2_PatchOnly, CI - Legacy OCAS Claim Adapters, ADW PRODUCER, Linux_Prod_Week3_PatchReboot, LMP ENGINEERING WORKSTATION, Linux_Prod_Week3_PatchOnlyVorm, Property/EB Reporting, AM-SPS DIAL, LM UNIVERSAL REINSURANCE SYSTEM, BUSINESS SERVICES - ESP, ADW REFERENCE, NESSUS SERVICES, eCLIQ 2.0, CENTRIFY SERVICES, TOBE Collections Cash Remittance, HS DATADOG, CENTRIFY LDAP PROXY, OC - AGENCY INFORMATION ARCH. | No | Yes, less than an hour | No | Moderate | Production (Prod) | LINUX SERVER TIER 1 | Rajiv Gandhi | AUTHORIZE | Normal
CHG07074234 | 2026/02/08 02:00:00 | 2026/02/08 08:00:00 | Need to reboot odprod on 08/02/2026 2AM to 8AM EST | CF, GDS, GRS, USRM | odprod, REINSURANCE DOCUMENT LIBRARY (RDL), ARMS Bill Scheduler, GRS OnDemand Request Daemon, VIA PAL Claims Correspondence, GRS OnDemand Notification Daemon, Managed Payments, Clipper | Yes | Yes, less than an hour | Yes | High | Production (Prod) | LINUX SERVER TIER 1 | Satheeshkumar Vaithilingam | AUTHORIZE | Normal
CHG07081313 | 2026/02/08 02:00:00 | 2026/02/08 05:00:00 | Permit access limited to LM Networks for olympus.libertymutual.com and prod2.olympus.libertymutual.com | USRM, GDS, GRS | AKAMAI, ES Buscador Nexus | No | Yes, less than an hour | No | Moderate | Production (Prod) | WAF AND CONTENT DELIVERY TIER 2 | Prasanth Katakam | AUTHORIZE | Normal
CHG06945303 | 2026/02/15 | 2026/02/15 08:45:00 | RDC - SYSA/SYSB - Upgrade SAS to V9.4TS1M8 | GRS, INV, CF, GDS, GCS, USRM | RDC-SYSA, RDC-SYSB, SAS 9.4, MXG 34.06 | No | Yes, less than an hour | Yes | Moderate | Production (Prod) | MAINFRAME SOFTWARE | VIJAY KOWSIK | NEW | Normal
CHG07085559 | 2026/02/15 06:00:00 | 2026/02/15 11:00:00 | Yearly Refresh of the Mainframe Certificates for Entrust Distrusted certificates in production OCG PROD01 | GCS, INV, GDS, USRM, CF, GRS | MAINFRAME PLATFORM COMPUTE SERVICES | No | Yes, less than an hour | Yes | Moderate | Production (Prod) | MAINFRAME SOFTWARE | Fernando Rodriguez | NEW | Normal

## Sheet3
CHG07038415 | LM UNIVERSAL REINSURANCE SYSTEM
CHG07075254 | CEDED REINSURANCE INVOICING AND BILLING SYSTEM (CRIBS),REINSURANCE DOCUMENT LIBRARY (RDL),CEDED REINSURANCE CONTRACT SYSTEM (CRCS),MANUAL CLAIM ENTRY (MCE)
CHG07074098 | LM UNIVERSAL REINSURANCE SYSTEM
CHG07074234 | REINSURANCE DOCUMENT LIBRARY (RDL)